## Group Members
REQUIREMENTS TRACEABILITY MATRIX (RTM)
VITAL: Virtual Interactive Telemedicine & Appointment Log
Bernardino General Hospital 1
Members: | Cruz, Cristian James A.
De Jesus, Gwyneth Viviene D.
Rivera, Adrian J.
Ulgasan, Baby Claire G.
Document Version Control
Document Information |  | Details
System Name |  | VITAL — Virtual Interactive Telemedicine & Appointment Log
Document Title |  | Requirements Traceability Matrix
Version |  | 4
Status |  | Final
Date |  | 2026-05-22
Prepared by: |  | Gwyneth De Jesus
Reviewed by: |  | Bernardino General Hospital I - IT Department
Approved by: |  | Ms. Michaela Alejandria - Industry Adviser
Adviser signature
Revision History
Version | Date | Description of Changes | Author
1 | 2026-04-11 | Initial Creation | Gwyneth De Jesus
2 | 2026-05-11 | Restructured product backlogs according to updated sprint schedule. Added compliance measures: RA 10173 (Philippine Data Privacy Act of 2012) including §20-21 breach notification, DOH DC 2020-0133 and JAO 2021-0001 on telemedicine guidelines, DOH MC 2020-0016 on referral and clinical documentation, DOH medical records retention guidelines, DOH-PhilHealth EMR data structure principles, FDA Circular 2020-037 on prescription validity, DICT/NPC security standards on authentication hardening, and PRC licensing requirements for doctor credential and prescription validation. | Gwyneth De Jesus
3 | 2026-05-20 | Generated burndown chart for sprint 0 and sprint 1 | Gwyneth De Jesus
4 | 2026-05-22 | Revised PB-018 and PB-023 to reflect the updated Doctor onboarding flow where Admins now create Doctor accounts directly instead of reviewing and approving submitted profile forms. PB-018 updated to capture the doctor's registration and profile form submission, flagged as 'Pending Doctor Account Setup.' PB-023 updated to cover Admin-initiated account creation, credential delivery via email, audit logging, and portal routing. FR-DOC-AUTH-001 and FR-ADM-USR-002 descriptions, notes, and acceptance criteria updated accordingly. RTM rows 44 and 63 aligned to reflect all FR changes. | Gwyneth De Jesus

## Backlogs
VITAL — Complete Product Backlog
Virtual Interactive Telemedicine & Appointment Log ¦ Bernardino General Hospital 1 ¦ 3 Development Sprints ¦ Team: 4 (1 PM, 1 BA, 2 Devs)
Backlog ID | Title | User Story | Role | Module | Acceptance Criteria | Priority | Effort (SP) | Target Sprint | Status | Assigned To | FRS Reference | Notes
SPRINT 0 — Requirements Gathering & Project Planning
PB-001 | Business Requirements Document (BRD) | As a project team, we need a BRD so that all stakeholders have a shared understanding of what VITAL must achieve. | Team | Documentation | • Covers executive summary, business objectives, project scope, system overview, module specs, sprint structure, assumptions, constraints, and success criteria • BRD complete and approved by all stakeholders • Sprint structure section reflects 3-sprint development plan (Sprint 1: May 12–19, Sprint 2: May 20–29, Sprint 3: May 30–June 15) | High | 8 | Sprint 0 | Done | Group | BRD | Completed.
PB-002 | Functional Requirements Specification (FRS) | As a project team, we need an FRS so that developers have a precise, testable specification of every system behavior. | Team | Documentation | • Covers all functional requirements per user role (Patient, Doctor, Admin, System) with inputs, outputs, business rules, and system behaviors • NFR section included • v3 reflects latest clarifications | High | 13 | Sprint 0 | Done | Group | FRS | Completed.
PB-003 | Product Backlog | As a project team, we need a Product Backlog so that all development work is itemized, prioritized, and ready for sprint planning. | Team | Documentation | • Backlog exists for all sprints (Sprint 0 through Sprint 3) • Each item has: ID, user story, role, module, acceptance criteria, priority, effort (SP), sprint target, and status • Reflects updated 3-sprint development structure | High | 5 | Sprint 0 | Done | Group | — | This document.
PB-004 | Context Diagram | As a project team, we need a Context Diagram so that external entities and system boundaries of VITAL are clearly visualized. | Team | System Diagrams | • Diagram shows VITAL as central system with all external entities and labelled data flows • External entities include: Patient, Doctor, Admin, UHSE, third-party video API, payment gateway (GCash/Maya), SMS/email provider | High | 3 | Sprint 0 | Done | Adrian | — | Completed.
PB-005 | Use Case Diagram | As a project team, we need a Use Case Diagram so that all system actors and their interactions with VITAL are captured. | Team | System Diagrams | • Covers all three roles (Patient, Doctor, Admin) and all major use cases • Relationships (include, extend) shown where applicable | High | 3 | Sprint 0 | Done | Adrian | — | Completed.
PB-006 | Data Flow Diagram (DFD) | As a project team, we need a DFD so that data movement between system components is documented. | Team | System Diagrams | • Covers Level 0 and Level 1 • All data stores, processes, and external entities labelled with correct data flow directions | High | 5 | Sprint 0 | Done | Adrian | — | Completed.
PB-007 | Workflow Diagram | As a project team, we need a Workflow Diagram so that end-to-end process flows are mapped out. | Team | System Diagrams | • Covers: registration, appointment booking lifecycle, pre-consultation, virtual consultation, and post-consultation steps | High | 5 | Sprint 0 | Done | Adrian | — | Completed.
PB-008 | Entity Relationship Diagram (ERD) | As a project team, we need an ERD so that the database structure and entity relationships are defined before development begins. | Team | System Diagrams | • Covers all major entities with relationships, cardinalities, and primary/foreign keys defined | High | 8 | Sprint 0 | Done | CJ | — | Completed.
PB-009 | Sprint Structure Definition | As a project team, we need a defined sprint structure so that development is organized into manageable increments. | Team | Sprint Planning | • Sprint structure defined: 3 development sprints across 6 weeks • Sprint 1: Foundation, Frontend Prototype & Authentication (May 12–19) • Sprint 2: Appointment Scheduling & Virtual Consultation (May 20–29) • Sprint 3: Records, Billing, Notifications & Integrations (May 30–June 15) • Each sprint has a phase name, key deliverables, and scope boundaries | High | 2 | Sprint 0 | Done | Group | BRD | Completed.
PB-010 | Stakeholder Analysis | As a project team, we need a stakeholder analysis so that all parties with interest in VITAL are identified. | Team | Sprint Planning | • Identifies all internal and external stakeholders, their roles, interests, and involvement level | High | 3 | Sprint 0 | Done | Claire | — | Completed.
PB-011 | Technology Stack Documentation | As a project team, we need a defined technology stack so that all members are aligned before Sprint 1 begins. | Team | Sprint Planning | • Documents: frontend framework, backend framework, database, third-party APIs (video conferencing, payment gateway, SMS/email provider) • Environment setup guide distributed to all team members • Unified with UHSE, TRACE, and AIMS coding standards | High | 3 | Sprint 0 | Done | CJ | — | Completed.
PB-012 | Project Repository & Version Control Setup | As a project team, we need a project repository and version control setup so that all code is tracked and collaborative development is possible. | Team | Sprint Planning | • Git repositories created and shared: vital-web and vital-services • Branching strategy defined • README with setup instructions present in both repositories | High | 2 | Sprint 0 | Done | CJ | — | Completed.
PB-013 | Coding Standards | As a project team, we need a defined coding standard so that the codebase remains consistent across all sprints. | Team | Sprint Planning | • Coding standards cover: naming conventions, file structure, commenting style, and API documentation format • Unified with UHSE, TRACE, and AIMS coding standards | Medium | 2 | Sprint 0 | Done | Group | — | Completed.
SPRINT 1 — Foundation, Frontend Prototype & Authentication
PB-014 | Patient Registration | As a patient, I want to register an account so I can access the Patient Portal. | Patient | Authentication | • Form collects: full name, email, password, contact number • Email validated for format; invalid format shows inline error • Password requires min. 8 characters with at least 1 uppercase, 1 lowercase, 1 number, 1 special character • Duplicate email rejected with message: 'An account with this email already exists' • Patient role assigned automatically on successful registration • Confirmation email sent upon successful account creation • UHSE credential lookup runs silently in background to pre-fill profile | High | 5 | Sprint 1 | To Do | Dev 2 | FR-PAT-AUTH-001
PB-015 | Patient Health Profile Completion | As a patient, I want to complete my health profile so I can unlock access to the Patient Portal. | Patient | Profile Management | • Required fields: Date of Birth, Sex, Home Address, PhilHealth ID • UHSE-matched fields (name, DOB, sex, PhilHealth ID) are pre-filled and locked with a lock icon and label; home address remains editable • External medical history form is always available regardless of UHSE match • Patient Portal access is blocked until all required fields are completed | High | 5 | Sprint 1 | To Do | Dev 2 | FR-PAT-AUTH-002
PB-016 | Patient Login & Session Management | As a patient, I want to log in and be routed to my portal so I can access my appointments and records. | Patient | Authentication | • Authenticated via email and password • On success: session token issued; patient routed exclusively to Patient Portal • Session expires after 30 minutes of inactivity • Failed login shows generic error (no specific reason disclosed) • Logged-in patient cannot access Doctor Portal or Admin Panel | High | 3 | Sprint 1 | To Do | Dev 2 | FR-PAT-AUTH-003 | Session timeout applies to all roles.
PB-017 | Patient Profile Update | As a patient, I want to update my personal details so my information stays current. | Patient | Profile Management | • Editable fields: profile photo, home address, contact number, emergency contact name and number, preferred communication channel (In-app, SMS, or Email) • Patient can add new external medical history records and edit self-submitted ones • UHSE-sourced and BGH clinical fields are read-only and cannot be modified | High | 5 | Sprint 1 | To Do | Dev 2 | FR-PAT-AUTH-004
PB-018 | Doctor Registration & Profile Form Submission | As a doctor, I want to register and submit my professional credentials so an admin can verify and assign my role. | Doctor | Authentication | • Doctor registers via the standard registration flow • After registration, doctor submits a Doctor Profile Form collecting: name, title/s, specialty, PRC license number (required), bio, availability type (Virtual/In-Person), virtual fee, in-person fee, affiliated hospitals, and contact information • Submitted form is flagged as 'Pending Doctor Account Setup' and Admin is notified • Doctor operates with limited access until Admin completes the Doctor account setup (see PB-023) • On first login after provisioning, doctor is routed to the Doctor Portal | High | 8 | Sprint 1 | To Do | Dev 2 | FR-DOC-AUTH-001
PB-019 | Doctor Login & Portal Routing | As a doctor, I want to log in and be routed to the Doctor Portal so I can manage my schedule and consultations. | Doctor | Authentication | • Doctor-role accounts authenticated and routed exclusively to Doctor Portal • Access to Patient Portal and Admin Panel is denied • Session expires after 30 minutes of inactivity | High | 3 | Sprint 1 | To Do | Dev 2 | FR-DOC-AUTH-002
PB-020 | Doctor Profile Update | As a doctor, I want to update my profile details so patients see accurate information when searching for me. | Doctor | Profile Management | • Editable fields: specialty, bio, availability type, virtual fee, in-person fee, affiliated hospitals, contact info • PRC license number and email are locked and cannot be modified • Profile changes reflected immediately on the public-facing profile card • Fee updates apply to future bookings only; existing confirmed bookings are unaffected | Medium | 5 | Sprint 1 | To Do | Dev 2 | FR-DOC-AUTH-003
PB-021 | Admin Login & Portal Routing | As an admin, I want to log in via UHSE credentials and access the Admin Panel. | Admin | Authentication | • Admin credentials validated via UHSE identity context • On success: Admin routed exclusively to Admin Panel • Access to Patient Portal and Doctor Portal is denied • Session expires after 30 minutes of inactivity • Generic error returned on failed login • Admin role provisioned by UHSE Superadmin only | High | 3 | Sprint 1 | To Do | Dev 2 | FR-ADM-AUTH-001
PB-022 | Admin User Search | As an admin, I want to search for Patient and Doctor accounts so I can manage user access. | Admin | User Management | • Search by: name, email, role, status • Results update dynamically as filters are applied • Admin accounts are excluded from search results • 'No users found' message shown when no accounts match | High | 3 | Sprint 1 | To Do | Dev 2 | FR-ADM-USR-001
PB-023 | Doctor Account Creation by Admin | As an admin, I want to create a doctor account so that I can grant verified doctors acccess to the Doctor Portal | Admin | User Management | • Admin can access a 'Create Doctor Account' form in the Admin Panel • Form requires the following fields: - Full Name, - PRC License Number, - Specialization, - Email Address, - Contact Number • PRC License Number is mandatory; the form cannot be submitted without it • On successful account creation, a Doctor account is provisioned, the action is logged in the audit log. • On first login, the doctor is routed to the Doctor Portal • Newly created doctor accounts appear in the Admin Panel under the Doctor Accounts list | High | 5 | Sprint 1 | To Do | Dev 2 | FR-ADM-USR-002
PB-024 | Account Deactivation | As an admin, I want to deactivate Patient or Doctor accounts so I can revoke access when needed. | Admin | User Management | • Deactivation requires a confirmation prompt before proceeding • On deactivation: account status set to 'Inactive', active session invalidated, user blocked from logging in • Deactivated user sees a clear message upon login attempt explaining account status • Accounts with existing records cannot be permanently deleted; historical data is retained • Deactivation action recorded in audit log | High | 5 | Sprint 1 | To Do | Dev 2 | FR-ADM-USR-003
PB-025 | Immutable Admin Audit Log | As an admin, I want every action I take to be automatically logged so there is a permanent record for accountability. | Admin | Audit Logging | • Every Admin action automatically generates an immutable log entry • Each entry contains: action type, target entity, timestamp, Admin user ID • Admin action logs retained for minimum 1 year; all other system access logs for minimum 90 days • Logs cannot be edited or deleted by any user • Audit log accessible to Admin role only | High | 5 | Sprint 1 | To Do | Dev 2 | FR-ADM-USR-004
PB-026 | Role-Based Access Control (RBAC) | As an admin, I want access to be restricted so that users can only reach features assigned to their role. | Admin | Security | • Patient accounts can only access the Patient Portal • Doctor accounts can only access the Doctor Portal • Admin accounts can only access the Admin Panel • Unauthorized route access is blocked and redirected • Role permissions checked on every request • HTTP connections rejected and automatically redirected to HTTPS | High | 8 | Sprint 1 | To Do | Dev 2 | FR-SYS-SEC-001 | Foundation for all portal access.
PB-027 | MFA for Doctor & Admin Accounts | As an admin, I want multi-factor authentication enforced for Doctor and Admin accounts to protect sensitive access. | Admin | Security | • MFA required on first login and when logging in from a new device or browser • Supported method: OTP via SMS or email • Doctor and Admin cannot complete login without passing MFA challenge • MFA bypass is not permitted under any condition | High | 5 | Sprint 1 | To Do | Dev 2 | FR-SYS-SEC-005
PB-028 | Login Lockout Policy | As an admin, I want accounts locked after repeated failed login attempts to prevent unauthorized access. | Admin | Security | • Account locked after 5 consecutive failed login attempts • Lockout duration: 15 minutes • User notified of lockout via email with unlock instructions • Failed attempt counter resets after successful login | High | 3 | Sprint 1 | To Do | Dev 2 | FR-SYS-SEC-006
PB-029 | Data Privacy Consent at Registration | As a patient, I want to be informed about the data privacy notice before completing registration so that I can make an informed decision about my data. | Patient | Compliance | • Checkbox at the bottom of the registration form labeled "I have read and understood the Data Privacy Notice" • "Data Privacy Notice" is a hyperlink opening the full informed consent content • Checkbox must be ticked before the form can be submitted • Attempting to submit without ticking shows an inline error message • Registration does not proceed if the checkbox is unticked • No consent record stored in the database, checkbox is a gate only | High | 3 | Sprint 1 | To Do | Dev 2 | FR-SYS-SEC-003
PB-030 | Admin KPI Dashboard (Mock) | As an admin, I want to see a dashboard when I log in so I have a central overview of system activity. | Admin | Dashboard | • Dashboard is the default landing screen upon Admin login • Displays mock data for: total users by role, active consultations, appointment trends, completion rates, recent audit entries, and quick-access links • Dashboard shell built in Sprint 1; live data connected in Sprint 3 • Each metric shows an error indicator if data fails to load | High | 5 | Sprint 1 | To Do | Dev 2 | FR-ADM-DSH-001 | Shell with mock data. Live data in Sprint 3.
PB-031 | Patient Dashboard (Static UI) | As a patient, I want to see a dashboard when I log in so I have a central overview of my portal. | Patient | Frontend — Static UI | • Static/mock UI built in Sprint 1; backend wiring in Sprint 3 • Displays: upcoming appointments summary, recent notifications, quick links to Find Doctors and Health Records | High | 3 | Sprint 1 | To Do | Dev 1 | — | Static UI only.
PB-032 | Appointments Screen (Static UI) | As a patient, I want to view my appointments screen so I can see and manage my consultations. | Patient | Frontend — Static UI | • Static/mock UI built in Sprint 1; backend wiring in Sprint 2 (PB-039) • Displays: list of appointments with status badges, filter controls (status, date range, doctor name) | High | 3 | Sprint 1 | To Do | Dev 1 | — | Static UI only.
PB-033 | Find Doctors Screen (Static UI) | As a patient, I want to browse and search for doctors so I can find one that fits my needs. | Patient | Frontend — Static UI | • Static/mock UI built in Sprint 1; backend wiring in Sprint 2 (PB-035) • Displays: search bar, filter controls, doctor profile cards with mock data | High | 3 | Sprint 1 | To Do | Dev 1 | — | Static UI only.
PB-034 | Doctor Profile & Schedule Screen (Static UI) | As a patient, I want to view a doctor's full profile and available schedule so I can decide to book. | Patient | Frontend — Static UI | • Static/mock UI built in Sprint 1; backend wiring in Sprint 2 • Displays: full name, title, specialty, bio, affiliated hospitals, availability type, fees, average star rating, and available schedule slots • Booking button visible; wired in Sprint 2 | High | 3 | Sprint 1 | To Do | Dev 1 | — | Static UI only.
SPRINT 2 — Appointment Scheduling & Virtual Consultation
PB-035 | Doctor Search | As a patient, I want to search for doctors so I can find one that matches my needs and availability. | Patient | Appointment Booking | • Wire backend to Find Doctors screen (built in Sprint 1 as PB-033) • Patient can search by: name, specialty, consultation type, and available date • Results update dynamically as filters are applied • Each result displays: full name, title, specialty, bio, affiliated hospitals, availability type, earliest slot, consultation fees, and average star rating • 'No doctors found' shown when no match • Only doctors with at least one published future slot appear in results | High | 5 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-001
PB-036 | Appointment Booking with Consent Prompt | As a patient, I want to book an appointment so I can consult with a doctor online. | Patient | Appointment Booking | • Patient selects a doctor, available slot, and consultation type before submitting • A medical record consent prompt is displayed on every booking without exception before the request is confirmed • Patient must actively accept the consent prompt; dismissing or closing it cancels the booking • On acceptance: appointment created as 'Pending', patient's health records shared with doctor, doctor notified • On decline: no appointment record created and no records shared; patient returned to scheduling screen • Consent record stored permanently with timestamp and linked to appointment; immutable • A slot already marked 'Booked' or 'Approved' cannot be selected | High | 8 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-002 | Consent prompt required on every booking.
PB-037 | Appointment Rescheduling | As a patient, I want to reschedule my approved appointment so I can adjust for changes in my availability. | Patient | Appointment Booking | • Rescheduling is only permitted for appointments with 'Approved' status • Patient selects a new future slot that is not already booked • Old slot is released upon rescheduling; new slot is set to 'Pending' and requires re-approval • Rescheduling within 1 hour of the scheduled time displays a warning prompt before confirmation • Both patient and doctor are notified with the updated appointment details | High | 3 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-003
PB-038 | Appointment Cancellation | As a patient, I want to cancel my appointment with a reason so the doctor is informed and the slot is freed. | Patient | Appointment Booking | • Patient must provide a cancellation reason before the cancellation is confirmed • Cancelling within 1 hour of the scheduled time displays a warning prompt • On confirmation: appointment status set to 'Cancelled', time slot released, doctor notified with cancellation reason • Cancelled appointments recorded in appointment history and are read-only | High | 3 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-004
PB-039 | Patient Appointment History | As a patient, I want to view my full appointment history so I can track all my past and current consultations. | Patient | Appointment Booking | • Wire backend to Appointments screen (built in Sprint 1 as PB-032) • Appointment history displays all appointments in chronological order with: doctor name, date/time, consultation type, status, and status transition log • Patient can filter by: status, date range, and doctor name • All status transitions visible: Pending, Approved, Rejected, Rescheduled, Cancelled, Completed • Appointment history records are read-only | Medium | 3 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-005
PB-040 | Doctor: Create & Publish Schedule Slots | As a doctor, I want to create and publish my consultation schedule so patients can see my availability and book. | Doctor | Schedule Management | • Doctor sets for each slot: date, start time, end time, consultation type (Virtual/In-Person), and maximum slot capacity • All fields required before a slot can be published • End time must be later than start time • Doctor cannot create two overlapping time slots on the same date; overlapping creation rejected with an error • At least one active GCash or Maya QR code must be on file before slots can be published • Published slots immediately visible to patients in Patient Portal | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-SCH-001
PB-041 | Doctor: Edit & Delete Schedule Slots | As a doctor, I want to edit or delete my schedule slots so I can update my availability when needed. | Doctor | Schedule Management | • Doctor can edit or delete existing schedule slots • Editing or deleting a slot with an existing approved booking requires a confirmation prompt and a cancellation reason • Affected patients automatically notified via SMS and/or email upon slot modification or deletion • Deletion of a slot with an approved booking is blocked until the doctor confirms and provides a cancellation reason | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-SCH-002
PB-042 | Doctor: Real-Time Pending Appointment Requests | As a doctor, I want to see all pending appointment requests in real time so I can act on them promptly. | Doctor | Appointment Management | • Pending appointment requests list displays: patient name, appointment date/time, consultation type, and any submitted chief complaint • List updates in real time • Only requests assigned to the logged-in doctor's own published schedule slots are shown | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-APT-001
PB-043 | Doctor: Approve or Reject Appointment Requests | As a doctor, I want to approve or reject appointment requests so I can confirm which consultations I will conduct. | Doctor | Appointment Management | • Doctor can approve a pending request; on approval the slot is marked 'Booked' and blocked from further patient requests • Doctor can reject a pending request; rejection requires a mandatory reason before the action is confirmed • On approval: patient notified immediately via SMS and/or email • On rejection: slot released, patient notified with the stated rejection reason • Appointment status updates reflected in real time in both Doctor Portal and Patient Portal | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-APT-002
PB-044 | Patient Pre-Consultation Form Submission | As a patient, I want to submit my credentials and chief complaint before my consultation so the doctor is prepared. | Patient | Pre-Consultation | • Pre-consultation form collects: Government ID (file upload, required), PhilHealth ID (file upload, required), chief complaint (min 10 characters, required), symptom duration (required), severity level (required), and relevant medical history summary (optional) • File uploads for Government ID and PhilHealth ID must be JPG, PNG, or PDF and must not exceed 5 MB per file • No general supporting document uploads are accepted at this stage • Submission must be completed at least 15 minutes before the scheduled consultation time • On successful submission, the doctor is notified that pre-consultation data is ready • A patient who has not completed pre-consultation submission cannot enter the waiting room • Validation failures display field-level errors without saving the submission | High | 5 | Sprint 2 | To Do | Dev 1 | FR-PAT-PRE-001
PB-045 | Doctor: View Pre-Consultation Data in Dashboard | As a doctor, I want to view a patient's pre-consultation submission so I can prepare before the session begins. | Doctor | Pre-Consultation | • Pre-consultation data is accessible from the upcoming appointment in the Doctor Portal • Doctor can view: patient name, submitted Government ID, PhilHealth ID, chief complaint, symptom duration, severity, and any relevant medical history • Pre-consultation data is only visible for appointments with 'Approved' status where the patient has completed the submission | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-APT-003
PB-046 | Patient Waiting Room & Auto-Transition to Live Call | As a patient, I want to join a waiting room and be automatically connected when my doctor starts the session. | Patient | Virtual Consultation | • Waiting room is accessible only for appointments with 'Approved' status and a completed pre-consultation submission • Patient sees a waiting room screen with appointment details and a real-time status indicator • Video call link generated by the system and delivered to both parties at least 30 minutes before the scheduled time • Patient is notified when the doctor joins and automatically transitioned to the live call • The system must not store or log any video or audio call content | High | 5 | Sprint 2 | To Do | Dev 1 | FR-PAT-CON-001
PB-046.1 | Waiting Room ↔ Video Session Integration Sync | As a user, I want the patient-side waiting room and doctor-side video initiation to be wired together so the end-to-end consultation flow works. | Patient / Doctor | Virtual Consultation | • Patient waiting room (PB-046) and doctor 'Start Session' (PB-049) connected end-to-end • Transition from waiting room to live call is seamless; no manual page refresh required • Integration tested with both portals running simultaneously • Target: Sprint 2, late sprint • Depends on: PB-046, PB-049, PB-053 | High | 5 | Sprint 2 | To Do | Dev 1 & Dev 2 | — | Integration sync task.
PB-047 | In-Session Ephemeral Document Sharing | As a patient or doctor, I want to share documents during the consultation without them being permanently stored. | Patient / Doctor | Virtual Consultation | • Patient and doctor can upload files via the in-session chatroom (PDF, JPG, PNG; max 10 MB per file) • Uploaded document is immediately visible to both parties within the consultation thread • Documents shared in-session are ephemeral — held in memory only and never written to the database • All in-session documents permanently purged when the session ends; neither party can retrieve them afterward • A notice is displayed within the session interface: 'Documents shared here are visible during this session only and will not be saved.' | High | 5 | Sprint 2 | To Do | Dev 1 | FR-PAT-CON-002 | Fully ephemeral — no storage.
PB-048 | Doctor: Patient Identity Verification at Session Start | As a doctor, I want to verify the patient's identity before beginning the consultation to comply with JAO 2021-0001. | Doctor | Virtual Consultation | • Doctor prompted to confirm patient identity at session start using the submitted Government ID • Consultation session cannot proceed until doctor confirms identity verification • Verification is logged with a timestamp and linked to the appointment record • Complies with JAO 2021-0001 identity verification requirement | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-CON-000
PB-049 | Doctor: Initiate Embedded Video Consultation | As a doctor, I want to start the video call directly within VITAL so patients are not redirected externally. | Doctor | Virtual Consultation | • Doctor clicks 'Start Session' at or after the scheduled appointment time to initiate the call • Video call initiated via the integrated third-party API; patient transitioned from waiting room to live call • Session is embedded within VITAL; no redirection to an external application occurs • Video call link can only be generated for appointments with 'Approved' status and a completed pre-consultation submission • The system must not store or log any video or audio content from the session | High | 8 | Sprint 2 | To Do | Dev 2 | FR-DOC-CON-001
PB-050 | Doctor: Side-Panel Note-Taking During Call | As a doctor, I want to take clinical notes alongside the video call so I can document findings without switching screens. | Doctor | Virtual Consultation | • A dedicated note-taking side panel is available alongside the video call during the consultation • Notes are auto-saved progressively without requiring manual save actions • Doctor can access the patient's pre-consultation data within the note-taking panel during the call | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-CON-002
PB-051 | Doctor: Finalize Consultation Report | As a doctor, I want to finalize and submit my consultation report so it is saved to the patient's health record. | Doctor | Virtual Consultation | • Doctor finalizes consultation report by entering: clinical findings (required), diagnosis (required), and at least one recommendation (required) • Attempting to finalize without all required fields returns a validation error • On finalization: report saved to patient's health record, made accessible to patient in Patient Portal, and appointment status updated to 'Completed' • Finalized report is immutable and cannot be edited after shared with the patient | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-CON-003
PB-052 | Auto-Generate Clinical Consultation Abstract | As an admin, I want the system to auto-generate a structured abstract on consultation finalization for DOH compliance and UHSE push. | Admin | Compliance | • Abstract auto-generated upon report finalization • Contains: patient name, VITAL system ID, consultation date, type, specialty, diagnosis, recommendations, and referring doctor if applicable • Abstract pushed to UHSE EHR system as part of the post-consultation sync • Complies with DOH telemedicine documentation requirements | High | 5 | Sprint 2 | To Do | Dev 2 | FR-SYS-DOC-001
PB-053 | Third-Party Video API Integration | As an admin, I want the system integrated with a third-party video conferencing API so virtual consultations can be conducted securely within VITAL. | Admin | Integrations | • System generates a secure video call link via the integrated third-party API for approved appointments with completed pre-consultation • Call link delivered to both patient and doctor at least 30 minutes before the scheduled time • Video session is embedded within VITAL; no redirection to an external application occurs • The system must not store or log any video or audio content from the session | High | 8 | Sprint 2 | To Do | Dev 2 | FR-SYS-INT-005
PB-054 | Emergency Care Disclaimer (DOH Compliance) | As an admin, I want the system to display a non-dismissible emergency care disclaimer to comply with DOH DC 2020-0133. | Admin | Compliance | • Non-dismissible emergency care disclaimer displayed on all consultation-related screens • Disclaimer text: 'VITAL is not an emergency service. If you are experiencing a medical emergency, call 911 or go to the nearest emergency room immediately.' • Cannot be hidden or bypassed by any user role • Complies with DOH DC 2020-0133 | High | 2 | Sprint 2 | To Do | Dev 2 | FR-SYS-CMP-001
PB-055 | Specialty-Scoped Consultation Restriction | As an admin, I want doctors to only conduct consultations within their verified specialty per JAO 2021-0001. | Admin | Compliance | • Doctor can only create schedule slots and accept bookings for consultations within their verified specialty • Patient cannot book a consultation type that falls outside the doctor's declared specialty • Specialty is set at Doctor Profile Form submission and locked unless updated by Admin • Complies with JAO 2021-0001 | High | 3 | Sprint 2 | To Do | Dev 2 | FR-SYS-CMP-002
PB-056 | Digital Prescription Issuance | As a doctor, I want to issue a digital prescription after a completed consultation so the patient can receive it electronically. | Doctor | Prescriptions | • Doctor issues a prescription with: medication name (required), dosage (required), frequency (required), duration (optional), and special instructions (optional) • Prescriptions can only be issued for appointments in 'Completed' status • Validity enforced: 1 week for antibiotics/antivirals/anti-infectives; 6 months for all others • Doctor's digital signature, PRC license number, and PTR number embedded on every prescription document • Issuance of S-2/PDEA-controlled dangerous drugs is blocked • System generates a globally unique alphanumeric access code for each prescription • Delivered to patient via SMS, email, and Patient Portal | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-PRX-001 | Buffer — can slide to Sprint 3.
PB-057 | Digital Medical Certificate Generation | As a doctor, I want to auto-generate a medical certificate from a completed consultation so the patient can use it officially. | Doctor | Prescriptions | • Auto-generated from consultation record upon doctor's request • Certificate contains: patient full name, date of consultation, diagnosis, doctor name, PRC license number • Only generatable for 'Completed' consultations • Delivered to patient via Patient Portal and SMS/email | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-PRX-002 | Buffer — can slide to Sprint 3.
PB-058 | Digital Referral Document | As a doctor, I want to issue a referral document when a patient needs in-person care so they have the proper documentation. | Doctor | Prescriptions | • Issuable for completed or ongoing consultations where physical examination or in-person care is required • Referral contains: patient name, consultation date, presenting complaint, provisional diagnosis, referring doctor's full name, specialty, and PRC license number • Delivered to patient via Patient Portal and SMS/email • Distinct from follow-up flag (per DOH MC 2020-0016) | Medium | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-REF-001 | Buffer — can slide to Sprint 3.
PB-059 | Follow-Up Flag on Completed Consultations | As a doctor, I want to flag a completed consultation as needing follow-up so the patient is reminded to rebook. | Doctor | Follow-Up | • Doctor can flag a completed consultation as requiring follow-up • A recommended follow-up timeframe (future date or defined period) is required when the flag is set • Flagging a non-completed consultation is rejected by the system • On flagging: patient notified via SMS, email, and in-app notification • Notification includes a direct link for the patient to rebook with the same doctor | Medium | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-FUP-001 | Buffer — can slide to Sprint 3.
SPRINT 3 — Records, Payments, Notifications, Integrations & Compliance
PB-060 | Unified Patient Health Records View | As a patient, I want to view all my health records in one place so I have a complete picture of my medical history. | Patient | Medical Records | • Dev 1 builds Health Records screen (static UI); Dev 2 wires backend • Records labelled by source: 'BGH/UHSE Record' (read-only) or 'External/Patient-Submitted' (editable) • BGH/UHSE Records include: diagnoses, prescriptions, consultation notes, and lab results • Filterable by: record type, source, and date range • Source labels are permanent and cannot be removed or altered • Only patient and doctors with explicit access can view the full health record | High | 8 | Sprint 3 | To Do | Dev 1 & Dev 2 | FR-PAT-REC-001
PB-061 | Patient-Controlled Health Record Access | As a patient, I want to control which doctors can see my health records so my data is only shared with my consent. | Patient | Medical Records | • Automatic path: doctor granted read-only access to patient's full health records when patient accepts the booking consent prompt • Manual path: patient can explicitly grant read-only access to an additional doctor outside the booking flow • Patient can revoke manually granted access at any time; access removed immediately upon revocation • Doctor access is read-only in all cases; shared doctor cannot edit any record • Each consent record stored permanently with timestamp; immutable | High | 5 | Sprint 3 | To Do | Dev 2 | FR-PAT-REC-002
PB-062 | Patient: View, Download & Retrieve Prescriptions and Medical Certificates | As a patient, I want to access and download my prescriptions and medical certificates at any time. | Patient | Medical Records | • Dev 1 builds Prescriptions & Medical Certificates screen (static UI); Dev 2 wires backend • Full list of issued prescriptions and medical certificates accessible from Patient Portal • Documents downloadable in PDF format • A valid unique alphanumeric access code retrieves and displays the corresponding document • An invalid or unknown code returns an error message • Expired prescriptions display a prominent warning with the expiry date but are not blocked • Documents accessible indefinitely; never automatically deleted | High | 5 | Sprint 3 | To Do | Dev 1 & Dev 2 | FR-PAT-REC-003, FR-SYS-PRX-001
PB-063 | Patient: Payment via GCash/Maya QR Code | As a patient, I want to pay for my consultation using GCash or Maya and submit proof of payment. | Patient | Payment | • Doctor's active GCash or Maya QR code displayed to patient at the payment step • Payment step accessible only for appointments with 'Approved' status • Patient submits proof of payment (JPG, PNG, or PDF; max 5 MB) and a mandatory payment reference number • On submission: appointment transitions to 'Pending Payment Verification' and doctor is notified • PhilHealth and insurance benefits do not apply to telemedicine consultations • VITAL does not process or handle funds at any point • Files outside accepted formats or exceeding 5 MB rejected with an error | High | 8 | Sprint 3 | To Do | Dev 1 | FR-PAT-PAY-001
PB-063.1 | Payment UI ↔ Payment Gateway Wiring Sync | As a user, I want the patient-side payment flow and the payment gateway integration to be connected so end-to-end payment works. | Patient / Doctor | Payment | • Patient QR code payment screen (PB-063) connected to gateway integration (PB-068) • Doctor payment proof approval (PB-067) triggers invoice generation (PB-065) • Payment status reflected correctly across both portals • Tested with both portals running simultaneously • Target: Sprint 3, late sprint (June 10–12) • Depends on: PB-063, PB-065, PB-067, PB-068 | High | 5 | Sprint 3 | To Do | Dev 1 & Dev 2 | — | Integration sync task.
PB-064 | Payment Approval/Rejection Notification & Invoice Generation | As a patient, I want to be notified when my payment is approved or rejected so I know the status of my booking. | Patient | Payment | • On payment approval: appointment updated to 'Confirmed'; patient notified via in-app and SMS/email • On payment rejection: appointment returned to resubmission-eligible state; patient notified with rejection reason | High | 3 | Sprint 3 | To Do | Dev 2 | FR-PAT-PAY-002
PB-065 | Auto-Generate PDF Invoice | As a patient, I want a downloadable invoice automatically generated when my payment is confirmed. | Patient | Payment | • Invoice auto-generated upon payment confirmation; no manual action required • Invoice contains: patient name, doctor name, consultation date, service, amount, payment method (GCash/Maya), and payment reference number • Available for download in PDF format from Patient Portal immediately after appointment marked 'Confirmed' • Invoices are read-only and cannot be edited or deleted | High | 3 | Sprint 3 | To Do | Dev 2 | FR-PAT-PAY-003
PB-066 | Doctor: Upload GCash/Maya QR Code | As a doctor, I want to upload my payment QR code so patients can pay me before consultations. | Doctor | Payment | • Doctor uploads GCash or Maya QR code image (JPG/PNG; max 5 MB) to their profile • At least one active QR code required before doctor can publish schedule slots • Doctor blocked from publishing slots if no active QR code exists • QR code associated with doctor's payment step and displayed to patients at checkout | High | 3 | Sprint 3 | To Do | Dev 2 | FR-DOC-PAY-001
PB-067 | Doctor: Approve or Reject Payment Proofs | As a doctor, I want to review and act on submitted payment proofs so I can confirm payment before conducting consultations. | Doctor | Payment | • Doctor can approve or reject a submitted proof of payment • On approval: internal payment record created, invoice generated automatically, patient notified • On rejection: rejection reason required before confirmation, patient notified with rejection reason, appointment returns to pending resubmission state | High | 5 | Sprint 3 | To Do | Dev 2 | FR-DOC-PAY-002
PB-068 | Payment Gateway Integration (GCash/Maya) | As an admin, I want all payment traffic to be secure and properly logged. | Admin | Integrations | • Payment processed via doctor's GCash or Maya QR code; VITAL does not independently process funds • All payment-related traffic occurs over HTTPS • VITAL does not store raw card or payment credential data • All transaction records logged with: timestamp, reference number, payment method, and amount; logs are immutable • On payment failure or rejected proof: clear error message shown and appointment not confirmed | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-INT-004
PB-069 | Multi-Channel Appointment Status Notifications | As a patient or doctor, I want to receive notifications for every appointment status change so I'm always up to date. | Patient / Doctor | Notifications | • Notification triggered for every status change: Pending, Approved, Rejected, Rescheduled, Cancelled, Completed • Delivered via SMS, email, and in-app to both relevant parties • Each notification includes: patient name, doctor name, appointment date/time, and new status • Dispatched within 5 minutes of the trigger event • Delivery failures logged and automatically retried at least once | High | 5 | Sprint 3 | To Do | Dev 2 | FR-SYS-NOT-001
PB-070 | Automated Appointment Reminders | As a patient or doctor, I want automated reminders before my consultation so I don't miss it. | Patient / Doctor | Notifications | • Automated reminders sent to both patient and doctor at 24 hours and 1 hour before each scheduled consultation • Delivered via SMS and email • Dispatched within 5 minutes of the trigger time; no manual intervention required • Cancelled or rescheduled appointments do not receive reminders for the original time slot | High | 5 | Sprint 3 | To Do | Dev 2 | FR-SYS-NOT-002
PB-071 | Secure Messaging Between Patient & Doctor | As a patient or doctor, I want to exchange secure messages outside the video session so we can communicate before and after consultations. | Patient / Doctor | Secure Messaging | • Dev 1 builds Messages screen (static UI); Dev 2 wires backend • Messaging permitted only between a patient and doctor who share an existing or upcoming appointment • Each message must not exceed 2,000 characters • All messages encrypted in transit using TLS 1.2 or higher • Messages stored and linked to the corresponding consultation record • Delivered to recipient's portal in real time with in-app and SMS/email notification • Doctor can send post-consultation follow-up care instructions via secure messaging | High | 5 | Sprint 3 | To Do | Dev 1 & Dev 2 | FR-PAT-MSG-001, FR-DOC-MSG-001
PB-072 | Bidirectional UHSE Integration | As an admin, I want the system to sync patient consultation records with UHSE to eliminate data silos. | Admin | Integrations | • Synchronization uses patient's unique VITAL system ID as the primary identifier • Sync occurs automatically after every completed consultation • Data conflicts flagged rather than silently overwritten • On UHSE API unavailability: sync queued and retried automatically when connection is restored | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-INT-001
PB-073 | UHSE EHR Integration — Push Finalized Records | As an admin, I want finalized consultation records, prescriptions, and medical certificates pushed to the UHSE EHR. | Admin | Integrations | • VITAL-generated records (consultation data, prescriptions, medical certificates) pushed to UHSE EHR system • All transmitted data linked using patient's unique VITAL system ID • On API unavailability: system displays a status indicator and queues sync for retry | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-INT-002
PB-074 | UHSE PMS Integration — Receive Lab Results | As an admin, I want the system to receive lab results from UHSE's Patient Management System and display them in the patient's health record. | Admin | Integrations | • Lab results received from UHSE PMS via API; displayed in patient health record without manual entry • Results mapped to correct patient using unique VITAL system ID • On API unavailability: status indicator displayed informing user that results may not be current | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-INT-003
PB-075 | Admin KPI Dashboard (Live Data) | As an admin, I want the dashboard to show live system data so I can monitor operations in real time. | Admin | Dashboard | • Live data wired up for: total users by role, active consultations, appointment trends, completion rates, recent audit log entries • Dashboard auto-refreshes every 5 minutes • Each metric shows an error indicator if data fails to load | High | 5 | Sprint 3 | To Do | Dev 2 | FR-ADM-DSH-001 | Live data connected here; shell built in Sprint 1.
PB-076 | System-Wide Report Generation | As an admin, I want to generate and export reports so I can analyze system performance and usage. | Admin | Analytics | • Admin can filter by: date range (required), module (optional), user type — Patient or Doctor (optional) • Exportable in PDF or Excel format • Each exported report includes a generation timestamp and generating admin's user ID • All data sourced from the system; no manual data entry required • Accessible to Admin role only | High | 5 | Sprint 3 | To Do | Dev 2 | FR-ADM-ANL-001
PB-077 | Per-Doctor Performance Metrics | As an admin, I want to view performance metrics per doctor so I can monitor service quality. | Admin | Analytics | • Displays per-doctor: total consultations handled, average patient star rating, total feedback count • Metrics aggregated from all completed consultations and associated patient feedback • Filterable by doctor name or date range • Read-only; admin cannot modify metrics | Medium | 3 | Sprint 3 | To Do | Dev 2 | FR-ADM-ANL-002
PB-078 | Admin: View All Patient Feedback | As an admin, I want to view all patient feedback across consultations so I can monitor service quality. | Admin | Feedback Management | • Displays all feedback entries: patient name, doctor name, consultation date, star rating, optional written feedback • Filterable by: doctor, date range, and star rating • Feedback records are read-only; admin cannot edit or delete • Accessible to Admin role only | Medium | 3 | Sprint 3 | To Do | Dev 2 | FR-ADM-FBK-001
PB-079 | Admin: System Content Management | As an admin, I want to publish announcements and FAQs so users see up-to-date information in their portals. | Admin | System Configuration | • Admin can create and update: announcements, FAQs, and other informational content • Published content immediately visible to users in the relevant portal section • Only Admin-role users can create or modify system content • All content changes recorded in audit log with timestamp and acting admin's user ID | Low | 3 | Sprint 3 | To Do | Dev 2 | FR-ADM-CFG-001
PB-080 | Post-Consultation Feedback Prompt | As a patient, I want to rate my consultation after it ends so I can share my experience with the hospital. | Patient | Feedback | • Patient prompted to submit feedback after consultation session ends • Star rating (1–5) is required; written feedback is optional • Only the attending patient can submit feedback for their own consultation • Only one submission per completed consultation; duplicate attempts rejected • Doctor's average rating updated immediately upon each new submission | High | 3 | Sprint 3 | To Do | Dev 1 | FR-PAT-FBK-001
PB-081 | AES-256 Encryption & TLS 1.2+ in Transit | As an admin, I want all patient health data encrypted at rest and in transit without exception. | Admin | Security | • All patient health data encrypted at rest using AES-256 • All data in transit encrypted using TLS 1.2 or higher; no exceptions for any data category • HTTP connections automatically rejected and redirected to HTTPS • Encryption implementation to be verified by security audit before final delivery | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-SEC-002
PB-082 | DOH Telemedicine Informed Consent | As an admin, I want DOH-mandated telemedicine informed consent collected before every first virtual consultation booking. | Admin | Compliance | • Separate from registration consent; displayed before every first virtual consultation booking • Discloses all five DOH-required points: how telemedicine works, how referral is conducted, privacy concerns, risk of technology failure and confidentiality breach, and policy on care coordination • Patient cannot proceed with booking without explicitly accepting • Consent record stored permanently with timestamp; immutable and retrievable for audit • Includes patient data portability and consent withdrawal rights | High | 5 | Sprint 3 | To Do | Dev 2 | FR-SYS-SEC-003
PB-083 | Immutable Data Access Logging | As an admin, I want all data access events logged and retained to support security audits. | Admin | Audit Logging | • All read, write, and delete events automatically logged: user ID, timestamp, action type, data entity accessed • Logs are immutable; cannot be edited or deleted by any user • Retained for minimum 90 days • Access log viewing restricted to Admin role only | High | 5 | Sprint 3 | To Do | Dev 2 | FR-SYS-SEC-004
PB-084 | Data Breach Monitoring & NPC Notification Workflow | As an admin, I want to detect anomalous access patterns and have a workflow to respond to data breaches per RA 10173. | Admin | Compliance | • System monitors data access logs for anomalous patterns (e.g., bulk record reads outside normal hours, access from unrecognized IPs) • Admin-role users automatically alerted on anomaly detection • Separate breach incident log maintained distinct from the standard audit log • Admin provided with a breach notification workflow to document: incident details, affected subjects, and NPC notification status • Supports RA 10173 §20-21 72-hour NPC notification requirement | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-BRN-001
PB-085 | Health Records Retention Enforcement | As an admin, I want patient health records retained for a minimum of 10 years per DOH guidelines. | Admin | Compliance | • No automated deletion or archival process removes records within a 10-year window from the last consultation • Deactivated patient accounts retain all historical health data • Verified by system configuration review before go-live | High | 3 | Sprint 3 | To Do | Dev 2 | NFR-COM-007
Total Items: 87 ¦ Total Story Points: 410

## Sprint 0
VITAL — Sprint 0 Backlog
Virtual Interactive Telemedicine & Appointment Log ¦ Bernardino General Hospital 1 ¦ 3 Development Sprints ¦ Team: 4 (1 PM, 1 BA, 2 Devs)
Backlog ID | Title | User Story | Role | Module | Acceptance Criteria | Priority | Effort (SP) | Target Sprint | Status | Assigned To | FRS Reference | Notes
SPRINT 0 — Requirements Gathering & Project Planning
PB-001 | Business Requirements Document (BRD) | As a project team, we need a BRD so that all stakeholders have a shared understanding of what VITAL must achieve. | Team | Documentation | • Covers executive summary, business objectives, project scope, system overview, module specs, sprint structure, assumptions, constraints, and success criteria • BRD complete and approved by all stakeholders • Sprint structure section reflects 3-sprint development plan (Sprint 1: May 12–19, Sprint 2: May 20–29, Sprint 3: May 30–June 15) | High | 8 | Sprint 0 | Done | Group | BRD | Completed.
PB-002 | Functional Requirements Specification (FRS) | As a project team, we need an FRS so that developers have a precise, testable specification of every system behavior. | Team | Documentation | • Covers all functional requirements per user role (Patient, Doctor, Admin, System) with inputs, outputs, business rules, and system behaviors • NFR section included • v3 reflects latest clarifications | High | 13 | Sprint 0 | Done | Group | FRS | Completed.
PB-003 | Product Backlog | As a project team, we need a Product Backlog so that all development work is itemized, prioritized, and ready for sprint planning. | Team | Documentation | • Backlog exists for all sprints (Sprint 0 through Sprint 3) • Each item has: ID, user story, role, module, acceptance criteria, priority, effort (SP), sprint target, and status • Reflects updated 3-sprint development structure | High | 5 | Sprint 0 | In Progress | Group | — | This document.
PB-004 | Context Diagram | As a project team, we need a Context Diagram so that external entities and system boundaries of VITAL are clearly visualized. | Team | System Diagrams | • Diagram shows VITAL as central system with all external entities and labelled data flows • External entities include: Patient, Doctor, Admin, UHSE, third-party video API, payment gateway (GCash/Maya), SMS/email provider | High | 3 | Sprint 0 | Done | Adrian | — | Completed.
PB-005 | Use Case Diagram | As a project team, we need a Use Case Diagram so that all system actors and their interactions with VITAL are captured. | Team | System Diagrams | • Covers all three roles (Patient, Doctor, Admin) and all major use cases • Relationships (include, extend) shown where applicable | High | 3 | Sprint 0 | Done | Adrian | — | Completed.
PB-006 | Data Flow Diagram (DFD) | As a project team, we need a DFD so that data movement between system components is documented. | Team | System Diagrams | • Covers Level 0 and Level 1 • All data stores, processes, and external entities labelled with correct data flow directions | High | 5 | Sprint 0 | Done | Adrian | — | Completed.
PB-007 | Workflow Diagram | As a project team, we need a Workflow Diagram so that end-to-end process flows are mapped out. | Team | System Diagrams | • Covers: registration, appointment booking lifecycle, pre-consultation, virtual consultation, and post-consultation steps | High | 5 | Sprint 0 | Done | Adrian | — | Completed.
PB-008 | Entity Relationship Diagram (ERD) | As a project team, we need an ERD so that the database structure and entity relationships are defined before development begins. | Team | System Diagrams | • Covers all major entities with relationships, cardinalities, and primary/foreign keys defined | High | 8 | Sprint 0 | Done | CJ | — | Completed.
PB-009 | Sprint Structure Definition | As a project team, we need a defined sprint structure so that development is organized into manageable increments. | Team | Sprint Planning | • Sprint structure defined: 3 development sprints across 6 weeks • Sprint 1: Foundation, Frontend Prototype & Authentication (May 12–19) • Sprint 2: Appointment Scheduling & Virtual Consultation (May 20–29) • Sprint 3: Records, Billing, Notifications & Integrations (May 30–June 15) • Each sprint has a phase name, key deliverables, and scope boundaries | High | 2 | Sprint 0 | Done | Group | BRD | Completed.
PB-010 | Stakeholder Analysis | As a project team, we need a stakeholder analysis so that all parties with interest in VITAL are identified. | Team | Sprint Planning | • Identifies all internal and external stakeholders, their roles, interests, and involvement level | High | 3 | Sprint 0 | Done | Claire | — | Completed.
PB-011 | Technology Stack Documentation | As a project team, we need a defined technology stack so that all members are aligned before Sprint 1 begins. | Team | Sprint Planning | • Documents: frontend framework, backend framework, database, third-party APIs (video conferencing, payment gateway, SMS/email provider) • Environment setup guide distributed to all team members • Unified with UHSE, TRACE, and AIMS coding standards | High | 3 | Sprint 0 | Done | CJ | — | Completed.
PB-012 | Project Repository & Version Control Setup | As a project team, we need a project repository and version control setup so that all code is tracked and collaborative development is possible. | Team | Sprint Planning | • Git repositories created and shared: vital-web and vital-services • Branching strategy defined • README with setup instructions present in both repositories | High | 2 | Sprint 0 | Done | CJ | — | Completed.
PB-013 | Coding Standards | As a project team, we need a defined coding standard so that the codebase remains consistent across all sprints. | Team | Sprint Planning | • Coding standards cover: naming conventions, file structure, commenting style, and API documentation format • Unified with UHSE, TRACE, and AIMS coding standards | Medium | 2 | Sprint 0 | Done | Group | — | Completed.
Total Items: 13 ¦ Total Story Points: 62

## Sprint 1
VITAL — Sprint 1 Backlog | [12 empty] | Progress Tracker
Phase: Foundation, Frontend Prototype & Authentication ¦ May 12–19, 2026 ¦ 8 Working Days ¦ Capacity: ~40 SP ¦ 2 Devs
Backlog ID | Title | User Story | Role | Module | Acceptance Criteria | Priority | Effort (SP) | Target Sprint | Status | Assigned To | FRS Reference | Notes | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22
SPRINT 1 — Foundation, Frontend Prototype & Authentication | [12 empty] | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
PB-014 | Patient Registration | As a patient, I want to register an account so I can access the Patient Portal. | Patient | Authentication | • Form collects: full name, email, password, contact number • Email validated for format; invalid format shows inline error • Password requires min. 8 characters with at least 1 uppercase, 1 lowercase, 1 number, 1 special character • Duplicate email rejected with message: 'An account with this email already exists' • Patient role assigned automatically on successful registration • Confirmation email sent upon successful account creation • UHSE credential lookup runs silently in background to pre-fill profile | High | 5 | Sprint 1 | EXECUTED | Dev 2 | FR-PAT-AUTH-001 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | CUT | 1 | 1
PB-015 | Patient Health Profile Completion | As a patient, I want to complete my health profile so I can unlock access to the Patient Portal. | Patient | Profile Management | • Required fields: Date of Birth, Sex, Home Address, PhilHealth ID • UHSE-matched fields (name, DOB, sex, PhilHealth ID) are pre-filled and locked with a lock icon and label; home address remains editable • External medical history form is always available regardless of UHSE match • Patient Portal access is blocked until all required fields are completed | High | 5 | Sprint 1 | EXECUTED | Dev 2 | FR-PAT-AUTH-002 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-016 | Patient Login & Session Management | As a patient, I want to log in and be routed to my portal so I can access my appointments and records. | Patient | Authentication | • Authenticated via email and password • On success: session token issued; patient routed exclusively to Patient Portal • Session expires after 30 minutes of inactivity • Failed login shows generic error (no specific reason disclosed) • Logged-in patient cannot access Doctor Portal or Admin Panel | High | 3 | Sprint 1 | EXECUTED | Dev 2 | FR-PAT-AUTH-003 | Session timeout applies to all roles. | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | CUT | 1 | 1
PB-017 | Patient Profile Update | As a patient, I want to update my personal details so my information stays current. | Patient | Profile Management | • Editable fields: profile photo, home address, contact number, emergency contact name and number, preferred communication channel (In-app, SMS, or Email) • Patient can add new external medical history records and edit self-submitted ones • UHSE-sourced and BGH clinical fields are read-only and cannot be modified | High | 5 | Sprint 1 | To Do | Dev 2 | FR-PAT-AUTH-004 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-018 | Doctor Account Registration | As a doctor, I want to register an account so that an admin can set up my Doctor profile and grant me access to the Doctor Portal. | Doctor | Authentication | • Doctor registers via the standard registration flow • After registration, doctor submits a Doctor Profile Form collecting: name, title/s, specialty, PRC license number (required), bio, availability type (Virtual/In-Person), virtual fee, in-person fee, affiliated hospitals, and contact information • Submitted form is flagged as 'Pending Doctor Account Setup' and Admin is notified • Doctor operates with limited access until Admin completes the Doctor account setup (see PB-023) • On first login after provisioning, doctor is routed to the Doctor Portal | High | 8 | Sprint 1 | To Do | Dev 2 | FR-DOC-AUTH-001 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-019 | Doctor Login & Portal Routing | As a doctor, I want to log in and be routed to the Doctor Portal so I can manage my schedule and consultations. | Doctor | Authentication | • Doctor-role accounts authenticated and routed exclusively to Doctor Portal • Access to Patient Portal and Admin Panel is denied • Session expires after 30 minutes of inactivity | High | 3 | Sprint 1 | EXECUTED | Dev 2 | FR-DOC-AUTH-002 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-020 | Doctor Profile Update | As a doctor, I want to update my profile details so patients see accurate information when searching for me. | Doctor | Profile Management | • Editable fields: specialty, bio, availability type, virtual fee, in-person fee, affiliated hospitals, contact info • PRC license number and email are locked and cannot be modified • Profile changes reflected immediately on the public-facing profile card • Fee updates apply to future bookings only; existing confirmed bookings are unaffected | Medium | 5 | Sprint 1 | To Do | Dev 2 | FR-DOC-AUTH-003 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-021 | Admin Login & Portal Routing | As an admin, I want to log in via UHSE credentials and access the Admin Panel. | Admin | Authentication | • Admin credentials validated via UHSE identity context • On success: Admin routed exclusively to Admin Panel • Access to Patient Portal and Doctor Portal is denied • Session expires after 30 minutes of inactivity • Generic error returned on failed login • Admin role provisioned by UHSE Superadmin only | High | 3 | Sprint 1 | EXECUTED | Dev 2 | FR-ADM-AUTH-001 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | CUT | 1 | 1
PB-022 | Admin User Search | As an admin, I want to search for Patient and Doctor accounts so I can manage user access. | Admin | User Management | • Search by: name, email, role, status • Results update dynamically as filters are applied • Admin accounts are excluded from search results • 'No users found' message shown when no accounts match | High | 3 | Sprint 1 | To Do | Dev 2 | FR-ADM-USR-001 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-023 | Doctor Account Creation by Admin | As an admin, I want to create a doctor account so that I can grant verified doctors acccess to the Doctor Portal | Admin | User Management | • Admin can access a 'Create Doctor Account' form in the Admin Panel • Form requires the following fields: - Full Name, - PRC License Number, - Specialization, - Email Address, - Contact Number • PRC License Number is mandatory; the form cannot be submitted without it • On successful account creation, a Doctor account is provisioned, the action is logged in the audit log. • On first login, the doctor is routed to the Doctor Portal • Newly created doctor accounts appear in the Admin Panel under the Doctor Accounts list | High | 5 | Sprint 1 | To Do | Dev 2 | FR-ADM-USR-002 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-024 | Account Deactivation | As an admin, I want to deactivate Patient or Doctor accounts so I can revoke access when needed. | Admin | User Management | • Deactivation requires a confirmation prompt before proceeding • On deactivation: account status set to 'Inactive', active session invalidated, user blocked from logging in • Deactivated user sees a clear message upon login attempt explaining account status • Accounts with existing records cannot be permanently deleted; historical data is retained • Deactivation action recorded in audit log | High | 5 | Sprint 1 | To Do | Dev 2 | FR-ADM-USR-003 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-025 | Immutable Admin Audit Log | As an admin, I want every action I take to be automatically logged so there is a permanent record for accountability. | Admin | Audit Logging | • Every Admin action automatically generates an immutable log entry • Each entry contains: action type, target entity, timestamp, Admin user ID • Admin action logs retained for minimum 1 year; all other system access logs for minimum 90 days • Logs cannot be edited or deleted by any user • Audit log accessible to Admin role only | High | 5 | Sprint 1 | To Do | Dev 2 | FR-ADM-USR-004 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-026 | Role-Based Access Control (RBAC) | As an admin, I want access to be restricted so that users can only reach features assigned to their role. | Admin | Security | • Patient accounts can only access the Patient Portal • Doctor accounts can only access the Doctor Portal • Admin accounts can only access the Admin Panel • Unauthorized route access is blocked and redirected • Role permissions checked on every request • HTTP connections rejected and automatically redirected to HTTPS | High | 8 | Sprint 1 | EXECUTED | Dev 2 | FR-SYS-SEC-001 | Foundation for all portal access. | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | CUT | 1 | 1
PB-027 | MFA for Doctor & Admin Accounts | As an admin, I want multi-factor authentication enforced for Doctor and Admin accounts to protect sensitive access. | Admin | Security | • MFA required on first login and when logging in from a new device or browser • Supported method: OTP via SMS or email • Doctor and Admin cannot complete login without passing MFA challenge • MFA bypass is not permitted under any condition | High | 5 | Sprint 1 | To Do | Dev 2 | FR-SYS-SEC-005 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-028 | Login Lockout Policy | As an admin, I want accounts locked after repeated failed login attempts to prevent unauthorized access. | Admin | Security | • Account locked after 5 consecutive failed login attempts • Lockout duration: 15 minutes • User notified of lockout via email with unlock instructions • Failed attempt counter resets after successful login | High | 3 | Sprint 1 | EXECUTED | Dev 2 | FR-SYS-SEC-006 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-029 | Data Privacy Consent at Registration | As a patient, I want to be informed about the data privacy notice before completing registration so that I can make an informed decision about my data. | Patient | Compliance | • Checkbox at the bottom of the registration form labeled "I have read and understood the Data Privacy Notice" • "Data Privacy Notice" is a hyperlink opening the full informed consent content • Checkbox must be ticked before the form can be submitted • Attempting to submit without ticking shows an inline error message • Registration does not proceed if the checkbox is unticked • No consent record stored in the database, checkbox is a gate only | High | 3 | Sprint 1 | EXECUTED | Dev 2 | FR-SYS-SEC-003 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-030 | Admin KPI Dashboard (Mock) | As an admin, I want to see a dashboard when I log in so I have a central overview of system activity. | Admin | Dashboard | • Dashboard is the default landing screen upon Admin login • Displays mock data for: total users by role, active consultations, appointment trends, completion rates, recent audit entries, and quick-access links • Dashboard shell built in Sprint 1; live data connected in Sprint 3 • Each metric shows an error indicator if data fails to load | High | 5 | Sprint 1 | EXECUTED | Dev 2 | FR-ADM-DSH-001 | Shell with mock data. Live data in Sprint 3. | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-031 | Patient Dashboard (Static UI) | As a patient, I want to see a dashboard when I log in so I have a central overview of my portal. | Patient | Frontend — Static UI | • Static/mock UI built in Sprint 1; backend wiring in Sprint 3 • Displays: upcoming appointments summary, recent notifications, quick links to Find Doctors and Health Records | High | 3 | Sprint 1 | EXECUTED | Dev 1 | — | Static UI only. | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-032 | Appointments Screen (Static UI) | As a patient, I want to view my appointments screen so I can see and manage my consultations. | Patient | Frontend — Static UI | • Static/mock UI built in Sprint 1; backend wiring in Sprint 2 (PB-039) • Displays: list of appointments with status badges, filter controls (status, date range, doctor name) | High | 3 | Sprint 1 | EXECUTED | Dev 1 | — | Static UI only. | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-033 | Find Doctors Screen (Static UI) | As a patient, I want to browse and search for doctors so I can find one that fits my needs. | Patient | Frontend — Static UI | • Static/mock UI built in Sprint 1; backend wiring in Sprint 2 (PB-035) • Displays: search bar, filter controls, doctor profile cards with mock data | High | 3 | Sprint 1 | EXECUTED | Dev 1 | — | Static UI only. | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PB-034 | Doctor Profile & Schedule Screen (Static UI) | As a patient, I want to view a doctor's full profile and available schedule so I can decide to book. | Patient | Frontend — Static UI | • Static/mock UI built in Sprint 1; backend wiring in Sprint 2 • Displays: full name, title, specialty, bio, affiliated hospitals, availability type, fees, average star rating, and available schedule slots • Booking button visible; wired in Sprint 2 | High | 3 | Sprint 1 | EXECUTED | Dev 1 | — | Static UI only. | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total Items: 21 ¦ Total Story Points: 91

## Sprint 2
VITAL — Sprint 2 Backlog | [12 empty] | Progress Tracker
Phase: Appointment Scheduling & Virtual Consultation ¦ May 20–29, 2026 ¦ 10 Working Days ¦ Capacity: ~50 SP ¦ 2 Devs | [12 empty] | Date
Backlog ID | Title | User Story | Role | Module | Acceptance Criteria | Priority | Effort (SP) | Target Sprint | Status | Assigned To | FRS Reference | Notes | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29
SPRINT 2 — Appointment Scheduling & Virtual Consultation | [12 empty] | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10
PB-035 | Doctor Search | As a patient, I want to search for doctors so I can find one that matches my needs and availability. | Patient | Appointment Booking | • Wire backend to Find Doctors screen (built in Sprint 1 as PB-033) • Patient can search by: name, specialty, consultation type, and available date • Results update dynamically as filters are applied • Each result displays: full name, title, specialty, bio, affiliated hospitals, availability type, earliest slot, consultation fees, and average star rating • 'No doctors found' shown when no match • Only doctors with at least one published future slot appear in results | High | 5 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-001
PB-036 | Appointment Booking with Consent Prompt | As a patient, I want to book an appointment so I can consult with a doctor online. | Patient | Appointment Booking | • Patient selects a doctor, available slot, and consultation type before submitting • A medical record consent prompt is displayed on every booking without exception before the request is confirmed • Patient must actively accept the consent prompt; dismissing or closing it cancels the booking • On acceptance: appointment created as 'Pending', patient's health records shared with doctor, doctor notified • On decline: no appointment record created and no records shared; patient returned to scheduling screen • Consent record stored permanently with timestamp and linked to appointment; immutable • A slot already marked 'Booked' or 'Approved' cannot be selected | High | 8 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-002 | Consent prompt required on every booking.
PB-037 | Appointment Rescheduling | As a patient, I want to reschedule my approved appointment so I can adjust for changes in my availability. | Patient | Appointment Booking | • Rescheduling is only permitted for appointments with 'Approved' status • Patient selects a new future slot that is not already booked • Old slot is released upon rescheduling; new slot is set to 'Pending' and requires re-approval • Rescheduling within 1 hour of the scheduled time displays a warning prompt before confirmation • Both patient and doctor are notified with the updated appointment details | High | 3 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-003
PB-038 | Appointment Cancellation | As a patient, I want to cancel my appointment with a reason so the doctor is informed and the slot is freed. | Patient | Appointment Booking | • Patient must provide a cancellation reason before the cancellation is confirmed • Cancelling within 1 hour of the scheduled time displays a warning prompt • On confirmation: appointment status set to 'Cancelled', time slot released, doctor notified with cancellation reason • Cancelled appointments recorded in appointment history and are read-only | High | 3 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-004
PB-039 | Patient Appointment History | As a patient, I want to view my full appointment history so I can track all my past and current consultations. | Patient | Appointment Booking | • Wire backend to Appointments screen (built in Sprint 1 as PB-032) • Appointment history displays all appointments in chronological order with: doctor name, date/time, consultation type, status, and status transition log • Patient can filter by: status, date range, and doctor name • All status transitions visible: Pending, Approved, Rejected, Rescheduled, Cancelled, Completed • Appointment history records are read-only | Medium | 3 | Sprint 2 | To Do | Dev 1 | FR-PAT-APT-005
PB-040 | Doctor: Create & Publish Schedule Slots | As a doctor, I want to create and publish my consultation schedule so patients can see my availability and book. | Doctor | Schedule Management | • Doctor sets for each slot: date, start time, end time, consultation type (Virtual/In-Person), and maximum slot capacity • All fields required before a slot can be published • End time must be later than start time • Doctor cannot create two overlapping time slots on the same date; overlapping creation rejected with an error • At least one active GCash or Maya QR code must be on file before slots can be published • Published slots immediately visible to patients in Patient Portal | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-SCH-001
PB-041 | Doctor: Edit & Delete Schedule Slots | As a doctor, I want to edit or delete my schedule slots so I can update my availability when needed. | Doctor | Schedule Management | • Doctor can edit or delete existing schedule slots • Editing or deleting a slot with an existing approved booking requires a confirmation prompt and a cancellation reason • Affected patients automatically notified via SMS and/or email upon slot modification or deletion • Deletion of a slot with an approved booking is blocked until the doctor confirms and provides a cancellation reason | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-SCH-002
PB-042 | Doctor: Real-Time Pending Appointment Requests | As a doctor, I want to see all pending appointment requests in real time so I can act on them promptly. | Doctor | Appointment Management | • Pending appointment requests list displays: patient name, appointment date/time, consultation type, and any submitted chief complaint • List updates in real time • Only requests assigned to the logged-in doctor's own published schedule slots are shown | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-APT-001
PB-043 | Doctor: Approve or Reject Appointment Requests | As a doctor, I want to approve or reject appointment requests so I can confirm which consultations I will conduct. | Doctor | Appointment Management | • Doctor can approve a pending request; on approval the slot is marked 'Booked' and blocked from further patient requests • Doctor can reject a pending request; rejection requires a mandatory reason before the action is confirmed • On approval: patient notified immediately via SMS and/or email • On rejection: slot released, patient notified with the stated rejection reason • Appointment status updates reflected in real time in both Doctor Portal and Patient Portal | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-APT-002
PB-044 | Patient Pre-Consultation Form Submission | As a patient, I want to submit my credentials and chief complaint before my consultation so the doctor is prepared. | Patient | Pre-Consultation | • Pre-consultation form collects: Government ID (file upload, required), PhilHealth ID (file upload, required), chief complaint (min 10 characters, required), symptom duration (required), severity level (required), and relevant medical history summary (optional) • File uploads for Government ID and PhilHealth ID must be JPG, PNG, or PDF and must not exceed 5 MB per file • No general supporting document uploads are accepted at this stage • Submission must be completed at least 15 minutes before the scheduled consultation time • On successful submission, the doctor is notified that pre-consultation data is ready • A patient who has not completed pre-consultation submission cannot enter the waiting room • Validation failures display field-level errors without saving the submission | High | 5 | Sprint 2 | To Do | Dev 1 | FR-PAT-PRE-001
PB-045 | Doctor: View Pre-Consultation Data in Dashboard | As a doctor, I want to view a patient's pre-consultation submission so I can prepare before the session begins. | Doctor | Pre-Consultation | • Pre-consultation data is accessible from the upcoming appointment in the Doctor Portal • Doctor can view: patient name, submitted Government ID, PhilHealth ID, chief complaint, symptom duration, severity, and any relevant medical history • Pre-consultation data is only visible for appointments with 'Approved' status where the patient has completed the submission | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-APT-003
PB-046 | Patient Waiting Room & Auto-Transition to Live Call | As a patient, I want to join a waiting room and be automatically connected when my doctor starts the session. | Patient | Virtual Consultation | • Waiting room is accessible only for appointments with 'Approved' status and a completed pre-consultation submission • Patient sees a waiting room screen with appointment details and a real-time status indicator • Video call link generated by the system and delivered to both parties at least 30 minutes before the scheduled time • Patient is notified when the doctor joins and automatically transitioned to the live call • The system must not store or log any video or audio call content | High | 5 | Sprint 2 | To Do | Dev 1 | FR-PAT-CON-001
PB-046.1 | Waiting Room ↔ Video Session Integration Sync | As a user, I want the patient-side waiting room and doctor-side video initiation to be wired together so the end-to-end consultation flow works. | Patient / Doctor | Virtual Consultation | • Patient waiting room (PB-046) and doctor 'Start Session' (PB-049) connected end-to-end • Transition from waiting room to live call is seamless; no manual page refresh required • Integration tested with both portals running simultaneously • Target: Sprint 2, late sprint • Depends on: PB-046, PB-049, PB-053 | High | 5 | Sprint 2 | To Do | Dev 1 & Dev 2 | — | Integration sync task.
PB-047 | In-Session Ephemeral Document Sharing | As a patient or doctor, I want to share documents during the consultation without them being permanently stored. | Patient / Doctor | Virtual Consultation | • Patient and doctor can upload files via the in-session chatroom (PDF, JPG, PNG; max 10 MB per file) • Uploaded document is immediately visible to both parties within the consultation thread • Documents shared in-session are ephemeral — held in memory only and never written to the database • All in-session documents permanently purged when the session ends; neither party can retrieve them afterward • A notice is displayed within the session interface: 'Documents shared here are visible during this session only and will not be saved.' | High | 5 | Sprint 2 | To Do | Dev 1 | FR-PAT-CON-002 | Fully ephemeral — no storage.
PB-048 | Doctor: Patient Identity Verification at Session Start | As a doctor, I want to verify the patient's identity before beginning the consultation to comply with JAO 2021-0001. | Doctor | Virtual Consultation | • Doctor prompted to confirm patient identity at session start using the submitted Government ID • Consultation session cannot proceed until doctor confirms identity verification • Verification is logged with a timestamp and linked to the appointment record • Complies with JAO 2021-0001 identity verification requirement | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-CON-000
PB-049 | Doctor: Initiate Embedded Video Consultation | As a doctor, I want to start the video call directly within VITAL so patients are not redirected externally. | Doctor | Virtual Consultation | • Doctor clicks 'Start Session' at or after the scheduled appointment time to initiate the call • Video call initiated via the integrated third-party API; patient transitioned from waiting room to live call • Session is embedded within VITAL; no redirection to an external application occurs • Video call link can only be generated for appointments with 'Approved' status and a completed pre-consultation submission • The system must not store or log any video or audio content from the session | High | 8 | Sprint 2 | To Do | Dev 2 | FR-DOC-CON-001
PB-050 | Doctor: Side-Panel Note-Taking During Call | As a doctor, I want to take clinical notes alongside the video call so I can document findings without switching screens. | Doctor | Virtual Consultation | • A dedicated note-taking side panel is available alongside the video call during the consultation • Notes are auto-saved progressively without requiring manual save actions • Doctor can access the patient's pre-consultation data within the note-taking panel during the call | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-CON-002
PB-051 | Doctor: Finalize Consultation Report | As a doctor, I want to finalize and submit my consultation report so it is saved to the patient's health record. | Doctor | Virtual Consultation | • Doctor finalizes consultation report by entering: clinical findings (required), diagnosis (required), and at least one recommendation (required) • Attempting to finalize without all required fields returns a validation error • On finalization: report saved to patient's health record, made accessible to patient in Patient Portal, and appointment status updated to 'Completed' • Finalized report is immutable and cannot be edited after shared with the patient | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-CON-003
PB-052 | Auto-Generate Clinical Consultation Abstract | As an admin, I want the system to auto-generate a structured abstract on consultation finalization for DOH compliance and UHSE push. | Admin | Compliance | • Abstract auto-generated upon report finalization • Contains: patient name, VITAL system ID, consultation date, type, specialty, diagnosis, recommendations, and referring doctor if applicable • Abstract pushed to UHSE EHR system as part of the post-consultation sync • Complies with DOH telemedicine documentation requirements | High | 5 | Sprint 2 | To Do | Dev 2 | FR-SYS-DOC-001
PB-053 | Third-Party Video API Integration | As an admin, I want the system integrated with a third-party video conferencing API so virtual consultations can be conducted securely within VITAL. | Admin | Integrations | • System generates a secure video call link via the integrated third-party API for approved appointments with completed pre-consultation • Call link delivered to both patient and doctor at least 30 minutes before the scheduled time • Video session is embedded within VITAL; no redirection to an external application occurs • The system must not store or log any video or audio content from the session | High | 8 | Sprint 2 | To Do | Dev 2 | FR-SYS-INT-005
PB-054 | Emergency Care Disclaimer (DOH Compliance) | As an admin, I want the system to display a non-dismissible emergency care disclaimer to comply with DOH DC 2020-0133. | Admin | Compliance | • Non-dismissible emergency care disclaimer displayed on all consultation-related screens • Disclaimer text: 'VITAL is not an emergency service. If you are experiencing a medical emergency, call 911 or go to the nearest emergency room immediately.' • Cannot be hidden or bypassed by any user role • Complies with DOH DC 2020-0133 | High | 2 | Sprint 2 | To Do | Dev 2 | FR-SYS-CMP-001
PB-055 | Specialty-Scoped Consultation Restriction | As an admin, I want doctors to only conduct consultations within their verified specialty per JAO 2021-0001. | Admin | Compliance | • Doctor can only create schedule slots and accept bookings for consultations within their verified specialty • Patient cannot book a consultation type that falls outside the doctor's declared specialty • Specialty is set at Doctor Profile Form submission and locked unless updated by Admin • Complies with JAO 2021-0001 | High | 3 | Sprint 2 | To Do | Dev 2 | FR-SYS-CMP-002
PB-056 | Digital Prescription Issuance | As a doctor, I want to issue a digital prescription after a completed consultation so the patient can receive it electronically. | Doctor | Prescriptions | • Doctor issues a prescription with: medication name (required), dosage (required), frequency (required), duration (optional), and special instructions (optional) • Prescriptions can only be issued for appointments in 'Completed' status • Validity enforced: 1 week for antibiotics/antivirals/anti-infectives; 6 months for all others • Doctor's digital signature, PRC license number, and PTR number embedded on every prescription document • Issuance of S-2/PDEA-controlled dangerous drugs is blocked • System generates a globally unique alphanumeric access code for each prescription • Delivered to patient via SMS, email, and Patient Portal | High | 5 | Sprint 2 | To Do | Dev 2 | FR-DOC-PRX-001 | Buffer — can slide to Sprint 3.
PB-057 | Digital Medical Certificate Generation | As a doctor, I want to auto-generate a medical certificate from a completed consultation so the patient can use it officially. | Doctor | Prescriptions | • Auto-generated from consultation record upon doctor's request • Certificate contains: patient full name, date of consultation, diagnosis, doctor name, PRC license number • Only generatable for 'Completed' consultations • Delivered to patient via Patient Portal and SMS/email | High | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-PRX-002 | Buffer — can slide to Sprint 3.
PB-058 | Digital Referral Document | As a doctor, I want to issue a referral document when a patient needs in-person care so they have the proper documentation. | Doctor | Prescriptions | • Issuable for completed or ongoing consultations where physical examination or in-person care is required • Referral contains: patient name, consultation date, presenting complaint, provisional diagnosis, referring doctor's full name, specialty, and PRC license number • Delivered to patient via Patient Portal and SMS/email • Distinct from follow-up flag (per DOH MC 2020-0016) | Medium | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-REF-001 | Buffer — can slide to Sprint 3.
PB-059 | Follow-Up Flag on Completed Consultations | As a doctor, I want to flag a completed consultation as needing follow-up so the patient is reminded to rebook. | Doctor | Follow-Up | • Doctor can flag a completed consultation as requiring follow-up • A recommended follow-up timeframe (future date or defined period) is required when the flag is set • Flagging a non-completed consultation is rejected by the system • On flagging: patient notified via SMS, email, and in-app notification • Notification includes a direct link for the patient to rebook with the same doctor | Medium | 3 | Sprint 2 | To Do | Dev 2 | FR-DOC-FUP-001 | Buffer — can slide to Sprint 3.
Total Items: 26 ¦ Total Story Points: 114

## Sprint 3
VITAL — Sprint 3 Backlog | [12 empty] | Progress Tracker
Phase: Records, Payments, Notifications, Integrations & Compliance ¦ May 30 – June 15, 2026 ¦ 17 Working Days ¦ Capacity: ~85 SP ¦ 2 Devs | [12 empty] | Date
Backlog ID | Title | User Story | Role | Module | Acceptance Criteria | Priority | Effort (SP) | Target Sprint | Status | Assigned To | FRS Reference | Notes | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15
SPRINT 3 — Records, Payments, Notifications, Integrations & Compliance | [12 empty] | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16 | DAY 17
PB-060 | Unified Patient Health Records View | As a patient, I want to view all my health records in one place so I have a complete picture of my medical history. | Patient | Medical Records | • Dev 1 builds Health Records screen (static UI); Dev 2 wires backend • Records labelled by source: 'BGH/UHSE Record' (read-only) or 'External/Patient-Submitted' (editable) • BGH/UHSE Records include: diagnoses, prescriptions, consultation notes, and lab results • Filterable by: record type, source, and date range • Source labels are permanent and cannot be removed or altered • Only patient and doctors with explicit access can view the full health record | High | 8 | Sprint 3 | To Do | Dev 1 & Dev 2 | FR-PAT-REC-001
PB-061 | Patient-Controlled Health Record Access | As a patient, I want to control which doctors can see my health records so my data is only shared with my consent. | Patient | Medical Records | • Automatic path: doctor granted read-only access to patient's full health records when patient accepts the booking consent prompt • Manual path: patient can explicitly grant read-only access to an additional doctor outside the booking flow • Patient can revoke manually granted access at any time; access removed immediately upon revocation • Doctor access is read-only in all cases; shared doctor cannot edit any record • Each consent record stored permanently with timestamp; immutable | High | 5 | Sprint 3 | To Do | Dev 2 | FR-PAT-REC-002
PB-062 | Patient: View, Download & Retrieve Prescriptions and Medical Certificates | As a patient, I want to access and download my prescriptions and medical certificates at any time. | Patient | Medical Records | • Dev 1 builds Prescriptions & Medical Certificates screen (static UI); Dev 2 wires backend • Full list of issued prescriptions and medical certificates accessible from Patient Portal • Documents downloadable in PDF format • A valid unique alphanumeric access code retrieves and displays the corresponding document • An invalid or unknown code returns an error message • Expired prescriptions display a prominent warning with the expiry date but are not blocked • Documents accessible indefinitely; never automatically deleted | High | 5 | Sprint 3 | To Do | Dev 1 & Dev 2 | FR-PAT-REC-003, FR-SYS-PRX-001
PB-063 | Patient: Payment via GCash/Maya QR Code | As a patient, I want to pay for my consultation using GCash or Maya and submit proof of payment. | Patient | Payment | • Doctor's active GCash or Maya QR code displayed to patient at the payment step • Payment step accessible only for appointments with 'Approved' status • Patient submits proof of payment (JPG, PNG, or PDF; max 5 MB) and a mandatory payment reference number • On submission: appointment transitions to 'Pending Payment Verification' and doctor is notified • PhilHealth and insurance benefits do not apply to telemedicine consultations • VITAL does not process or handle funds at any point • Files outside accepted formats or exceeding 5 MB rejected with an error | High | 8 | Sprint 3 | To Do | Dev 1 | FR-PAT-PAY-001
PB-063.1 | Payment UI ↔ Payment Gateway Wiring Sync | As a user, I want the patient-side payment flow and the payment gateway integration to be connected so end-to-end payment works. | Patient / Doctor | Payment | • Patient QR code payment screen (PB-063) connected to gateway integration (PB-068) • Doctor payment proof approval (PB-067) triggers invoice generation (PB-065) • Payment status reflected correctly across both portals • Tested with both portals running simultaneously • Target: Sprint 3, late sprint (June 10–12) • Depends on: PB-063, PB-065, PB-067, PB-068 | High | 5 | Sprint 3 | To Do | Dev 1 & Dev 2 | — | Integration sync task.
PB-064 | Payment Approval/Rejection Notification & Invoice Generation | As a patient, I want to be notified when my payment is approved or rejected so I know the status of my booking. | Patient | Payment | • On payment approval: appointment updated to 'Confirmed'; patient notified via in-app and SMS/email • On payment rejection: appointment returned to resubmission-eligible state; patient notified with rejection reason | High | 3 | Sprint 3 | To Do | Dev 2 | FR-PAT-PAY-002
PB-065 | Auto-Generate PDF Invoice | As a patient, I want a downloadable invoice automatically generated when my payment is confirmed. | Patient | Payment | • Invoice auto-generated upon payment confirmation; no manual action required • Invoice contains: patient name, doctor name, consultation date, service, amount, payment method (GCash/Maya), and payment reference number • Available for download in PDF format from Patient Portal immediately after appointment marked 'Confirmed' • Invoices are read-only and cannot be edited or deleted | High | 3 | Sprint 3 | To Do | Dev 2 | FR-PAT-PAY-003
PB-066 | Doctor: Upload GCash/Maya QR Code | As a doctor, I want to upload my payment QR code so patients can pay me before consultations. | Doctor | Payment | • Doctor uploads GCash or Maya QR code image (JPG/PNG; max 5 MB) to their profile • At least one active QR code required before doctor can publish schedule slots • Doctor blocked from publishing slots if no active QR code exists • QR code associated with doctor's payment step and displayed to patients at checkout | High | 3 | Sprint 3 | To Do | Dev 2 | FR-DOC-PAY-001
PB-067 | Doctor: Approve or Reject Payment Proofs | As a doctor, I want to review and act on submitted payment proofs so I can confirm payment before conducting consultations. | Doctor | Payment | • Doctor can approve or reject a submitted proof of payment • On approval: internal payment record created, invoice generated automatically, patient notified • On rejection: rejection reason required before confirmation, patient notified with rejection reason, appointment returns to pending resubmission state | High | 5 | Sprint 3 | To Do | Dev 2 | FR-DOC-PAY-002
PB-068 | Payment Gateway Integration (GCash/Maya) | As an admin, I want all payment traffic to be secure and properly logged. | Admin | Integrations | • Payment processed via doctor's GCash or Maya QR code; VITAL does not independently process funds • All payment-related traffic occurs over HTTPS • VITAL does not store raw card or payment credential data • All transaction records logged with: timestamp, reference number, payment method, and amount; logs are immutable • On payment failure or rejected proof: clear error message shown and appointment not confirmed | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-INT-004
PB-069 | Multi-Channel Appointment Status Notifications | As a patient or doctor, I want to receive notifications for every appointment status change so I'm always up to date. | Patient / Doctor | Notifications | • Notification triggered for every status change: Pending, Approved, Rejected, Rescheduled, Cancelled, Completed • Delivered via SMS, email, and in-app to both relevant parties • Each notification includes: patient name, doctor name, appointment date/time, and new status • Dispatched within 5 minutes of the trigger event • Delivery failures logged and automatically retried at least once | High | 5 | Sprint 3 | To Do | Dev 2 | FR-SYS-NOT-001
PB-070 | Automated Appointment Reminders | As a patient or doctor, I want automated reminders before my consultation so I don't miss it. | Patient / Doctor | Notifications | • Automated reminders sent to both patient and doctor at 24 hours and 1 hour before each scheduled consultation • Delivered via SMS and email • Dispatched within 5 minutes of the trigger time; no manual intervention required • Cancelled or rescheduled appointments do not receive reminders for the original time slot | High | 5 | Sprint 3 | To Do | Dev 2 | FR-SYS-NOT-002
PB-071 | Secure Messaging Between Patient & Doctor | As a patient or doctor, I want to exchange secure messages outside the video session so we can communicate before and after consultations. | Patient / Doctor | Secure Messaging | • Dev 1 builds Messages screen (static UI); Dev 2 wires backend • Messaging permitted only between a patient and doctor who share an existing or upcoming appointment • Each message must not exceed 2,000 characters • All messages encrypted in transit using TLS 1.2 or higher • Messages stored and linked to the corresponding consultation record • Delivered to recipient's portal in real time with in-app and SMS/email notification • Doctor can send post-consultation follow-up care instructions via secure messaging | High | 5 | Sprint 3 | To Do | Dev 1 & Dev 2 | FR-PAT-MSG-001, FR-DOC-MSG-001
PB-072 | Bidirectional UHSE Integration | As an admin, I want the system to sync patient consultation records with UHSE to eliminate data silos. | Admin | Integrations | • Synchronization uses patient's unique VITAL system ID as the primary identifier • Sync occurs automatically after every completed consultation • Data conflicts flagged rather than silently overwritten • On UHSE API unavailability: sync queued and retried automatically when connection is restored | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-INT-001
PB-073 | UHSE EHR Integration — Push Finalized Records | As an admin, I want finalized consultation records, prescriptions, and medical certificates pushed to the UHSE EHR. | Admin | Integrations | • VITAL-generated records (consultation data, prescriptions, medical certificates) pushed to UHSE EHR system • All transmitted data linked using patient's unique VITAL system ID • On API unavailability: system displays a status indicator and queues sync for retry | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-INT-002
PB-074 | UHSE PMS Integration — Receive Lab Results | As an admin, I want the system to receive lab results from UHSE's Patient Management System and display them in the patient's health record. | Admin | Integrations | • Lab results received from UHSE PMS via API; displayed in patient health record without manual entry • Results mapped to correct patient using unique VITAL system ID • On API unavailability: status indicator displayed informing user that results may not be current | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-INT-003
PB-075 | Admin KPI Dashboard (Live Data) | As an admin, I want the dashboard to show live system data so I can monitor operations in real time. | Admin | Dashboard | • Live data wired up for: total users by role, active consultations, appointment trends, completion rates, recent audit log entries • Dashboard auto-refreshes every 5 minutes • Each metric shows an error indicator if data fails to load | High | 5 | Sprint 3 | To Do | Dev 2 | FR-ADM-DSH-001 | Live data connected here; shell built in Sprint 1.
PB-076 | System-Wide Report Generation | As an admin, I want to generate and export reports so I can analyze system performance and usage. | Admin | Analytics | • Admin can filter by: date range (required), module (optional), user type — Patient or Doctor (optional) • Exportable in PDF or Excel format • Each exported report includes a generation timestamp and generating admin's user ID • All data sourced from the system; no manual data entry required • Accessible to Admin role only | High | 5 | Sprint 3 | To Do | Dev 2 | FR-ADM-ANL-001
PB-077 | Per-Doctor Performance Metrics | As an admin, I want to view performance metrics per doctor so I can monitor service quality. | Admin | Analytics | • Displays per-doctor: total consultations handled, average patient star rating, total feedback count • Metrics aggregated from all completed consultations and associated patient feedback • Filterable by doctor name or date range • Read-only; admin cannot modify metrics | Medium | 3 | Sprint 3 | To Do | Dev 2 | FR-ADM-ANL-002
PB-078 | Admin: View All Patient Feedback | As an admin, I want to view all patient feedback across consultations so I can monitor service quality. | Admin | Feedback Management | • Displays all feedback entries: patient name, doctor name, consultation date, star rating, optional written feedback • Filterable by: doctor, date range, and star rating • Feedback records are read-only; admin cannot edit or delete • Accessible to Admin role only | Medium | 3 | Sprint 3 | To Do | Dev 2 | FR-ADM-FBK-001
PB-079 | Admin: System Content Management | As an admin, I want to publish announcements and FAQs so users see up-to-date information in their portals. | Admin | System Configuration | • Admin can create and update: announcements, FAQs, and other informational content • Published content immediately visible to users in the relevant portal section • Only Admin-role users can create or modify system content • All content changes recorded in audit log with timestamp and acting admin's user ID | Low | 3 | Sprint 3 | To Do | Dev 2 | FR-ADM-CFG-001
PB-080 | Post-Consultation Feedback Prompt | As a patient, I want to rate my consultation after it ends so I can share my experience with the hospital. | Patient | Feedback | • Patient prompted to submit feedback after consultation session ends • Star rating (1–5) is required; written feedback is optional • Only the attending patient can submit feedback for their own consultation • Only one submission per completed consultation; duplicate attempts rejected • Doctor's average rating updated immediately upon each new submission | High | 3 | Sprint 3 | To Do | Dev 1 | FR-PAT-FBK-001
PB-081 | AES-256 Encryption & TLS 1.2+ in Transit | As an admin, I want all patient health data encrypted at rest and in transit without exception. | Admin | Security | • All patient health data encrypted at rest using AES-256 • All data in transit encrypted using TLS 1.2 or higher; no exceptions for any data category • HTTP connections automatically rejected and redirected to HTTPS • Encryption implementation to be verified by security audit before final delivery | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-SEC-002
PB-082 | DOH Telemedicine Informed Consent | As an admin, I want DOH-mandated telemedicine informed consent collected before every first virtual consultation booking. | Admin | Compliance | • Separate from registration consent; displayed before every first virtual consultation booking • Discloses all five DOH-required points: how telemedicine works, how referral is conducted, privacy concerns, risk of technology failure and confidentiality breach, and policy on care coordination • Patient cannot proceed with booking without explicitly accepting • Consent record stored permanently with timestamp; immutable and retrievable for audit • Includes patient data portability and consent withdrawal rights | High | 5 | Sprint 3 | To Do | Dev 2 | FR-SYS-SEC-003
PB-083 | Immutable Data Access Logging | As an admin, I want all data access events logged and retained to support security audits. | Admin | Audit Logging | • All read, write, and delete events automatically logged: user ID, timestamp, action type, data entity accessed • Logs are immutable; cannot be edited or deleted by any user • Retained for minimum 90 days • Access log viewing restricted to Admin role only | High | 5 | Sprint 3 | To Do | Dev 2 | FR-SYS-SEC-004
PB-084 | Data Breach Monitoring & NPC Notification Workflow | As an admin, I want to detect anomalous access patterns and have a workflow to respond to data breaches per RA 10173. | Admin | Compliance | • System monitors data access logs for anomalous patterns (e.g., bulk record reads outside normal hours, access from unrecognized IPs) • Admin-role users automatically alerted on anomaly detection • Separate breach incident log maintained distinct from the standard audit log • Admin provided with a breach notification workflow to document: incident details, affected subjects, and NPC notification status • Supports RA 10173 §20-21 72-hour NPC notification requirement | High | 8 | Sprint 3 | To Do | Dev 2 | FR-SYS-BRN-001
PB-085 | Health Records Retention Enforcement | As an admin, I want patient health records retained for a minimum of 10 years per DOH guidelines. | Admin | Compliance | • No automated deletion or archival process removes records within a 10-year window from the last consultation • Deactivated patient accounts retain all historical health data • Verified by system configuration review before go-live | High | 3 | Sprint 3 | To Do | Dev 2 | NFR-COM-007
Total Items: 27 ¦ Total Story Points: 143

## Legend
VITAL Product Backlog — Legend
Priority
High | Must be delivered this sprint — blocking or critical path.
Medium | Important but not blocking. Deliver if capacity allows.
Low | Nice to have. Can be deferred without impacting core functionality.
Status
Done | Completed and verified.
In Progress | Currently being worked on.
To Do | Not yet started.
Role Tag
Patient | Requirement applies to the Patient role.
Doctor | Requirement applies to the Doctor role.
Admin | Requirement applies to the Admin role or is a system-level cross-cutting concern.
Patient / Doctor | Applies to both Patient and Doctor roles.
Team | Project team planning/documentation deliverable — not a code feature.
Sprint
Sprint 0 | Requirements gathering, diagrams, planning — March 29 – April 12, 2026.
Sprint 1 | Foundation, frontend prototype, authentication — May 12–19, 2026.
Sprint 2 | Appointment scheduling, virtual consultation, prescriptions — May 20–29, 2026.
Sprint 3 | Records, payments, notifications, integrations, compliance — May 30–June 15, 2026.
Effort (SP)
1–2 SP | Trivial — simple config, minor UI, or documentation update.
3–5 SP | Small — straightforward feature with clear requirements.
8 SP | Medium — multi-step feature with integration or validation logic.
13 SP | Large — complex feature spanning multiple components or roles.
Assigned To
Dev 1 | Frontend developer — builds patient-facing static UI screens.
Dev 2 | Full-stack developer — handles auth, backend wiring, and system-level features.
Dev 1 & Dev 2 | Both developers collaborate on this item.
Group | Entire project team.
Claire | Project Manager / BA.
Gwen | Business Analyst / Documentation lead.
Adrian | System Diagrams lead.
CJ | Dev 2 / Repository & infrastructure lead.

## Links
VITAL Links
RTM | https://1drv.ms/x/c/050864FD1DE63622/IQDBzYeCSCRpR7vEH3Rn1nBcASontYMUz1MFTQu1cW2aXbc?e=FyUmkx
BRD | https://docs.google.com/document/d/1Y9eutyd5c59SShbVSBQz1qr-nzrBTv4goiDg9bVWGLs/edit?usp=sharing
FRD
JIRA | https://projectvital.atlassian.net/jira/software/projects/VIT/boards/2/backlog?atlOrigin=eyJpIjoiOTkzMGQyY2MzM2RhNDM5NzhkMjhkYzkxMzBiODAyMWYiLCJwIjoiaiJ9
REPO | https://github.com/CJ-Zurc/vital-web.git https://github.com/CJ-Zurc/vital-services.git
DIAGRAMS | https://drive.google.com/drive/folders/1V2oZBMYbbSkB2DNlB5H5CuA99hrBxQ4e?usp=drive_link

## Burndown
VITAL BURNDOWN CHART
Date/Sprint | Ideal Remaining | Actual Remaining | Completed
Sprint 0 (March 29) | 385 | 385
Sprint 0 end (April 12) | 289 | 323 | 62
Sprint 1 end (May 19) | 193 | 194 | 34
Sprint 2 end (May 29) | 97
Sprint 3 end (June 15)
Formulas
Ideal remaining |  | Previous Ideal Remaining − (Total SP ÷ Number of Sprints)
Actual remaining |  | Actual Remaining = Previous Actual Remaining − Completed SP this sprint
Completed |  | Completed = Previous Actual Remaining − Current Actual Remaining